## Sheet1
Database Row # | Print / Export Record | *Insp. Type | *Inspection Date / Inspector | *Address | *Unit | *Bldg. Visual Unit | *Street | *Bldg. | *Phase | *Plan Type | *Design Type | PPT | Exemplar | *Issue | Cladding | Component | Observation | *Room | *Elevation | Location | Extent | LF | SF | Ct. (Total) | *Penetration Type | *Window Type | *Door Type | Custom1 | Custom2 | Photo Path
1 | FALSE | Int._Ext. Vis. | 2024-10-01 MH Int_Ext Vis | 1234 |  |  | Madera | 1 | 2B | 1 |  | FALSE | FALSE | 3.01a Stucco cracks; spalling |  |  | Cracks |  | Front | Wall | HL to 1/32" | 100 |  | 25
2 | FALSE | Int._Ext. Vis. | 2024-10-01 MH Int_Ext Vis | 1345 |  |  | Madera | 1 | 2B | 1 |  | FALSE | TRUE | 3.01a Stucco cracks; spalling |  |  | Cracks; spalling |  | Front | Soffit | 1/16" (w/ 1/2" spalling) | 2 |  | 1 | [5 empty] | /Dropbox/Projects/Avala/05 Photos/Avala 2024-10-01 MH Int
3 | FALSE | Int._Ext. Vis. | 2024-10-01 MH Int_Ext Vis | 1456 |  |  | San Diego Street | 5 | 3A | 2 |  | FALSE | FALSE | 5.02 Door finish failure; paint delamination; corrosion |  |  | Paint weathered; faded | Entry | Left |  | 100% |  |  | 1 |  |  | Hollow Mtl Dr. |  |  | /Dropbox/Projects/Avala/05 Photos/Avala 2024-10-01 MH Int Vis
4 | TRUE | Int. Vis. | 2025-06-14 MH Int Vis | 1567 |  |  | San Diego Street | 6 | 3A | 2 |  | FALSE | FALSE | 4.01a Gyp. bd. crack; joint separation; tape delamination; failed repairs |  |  | Tape delam. | Liv. Rm. |  | Clg. (adj. outside wall corner) | 1/32" | 3.5 |  | 2 | [5 empty] | /Dropbox/Projects/Avala/05 Photos/Avala 2025-06-14 MH Int Vis
5 | TRUE | Int. Vis. | 2025-06-14 MH Int Vis | 1678 |  |  | La Jolla Drive | 7 | 1 | 3AR | 1-A-B-R | FALSE | FALSE | 4.03 Lap siding and wood trim in contact with concrete and/or grade | Siding | Conc. | Buried |  | Rear | Adj entry door |  | 6 |  | 2 | [5 empty] | /Dropbox/Projects/Avala/05 Photos/Avala 2025-06-14 MH Int Vis
6 | TRUE | Int. Vis. | 2025-06-14 MH Int Vis | 1678 |  |  | La Jolla Drive | 7 | 1 | 3AR | 1-A-B-R | TRUE | TRUE | 4.04 Lap siding warped |  |  | Warped |  | Right | Wall plane | 2nd flr adj. to previously repair locations with inadeq. paint finish |  | 250 | 10 | [5 empty] | /Dropbox/Projects/Avala/05 Photos/Avala 2025-06-14 MH Int Vis
7 | TRUE | Roof Vis. | 2024-12-12 BS Roof Vis |  |  |  |  | 4 |  |  |  | TRUE | TRUE | 2.01 Roof penetration unsealed | [9 empty] | 3 | P-vent |  |  |  |  | /Dropbox/Projects/Avala/05 Photos/Avala 2024-12-12 BS Roof Vis
8 | FALSE | Ext. Vis. | 2024-10-25 PKE Ext Vis | 3456 | 101 |  | California Ave. | 10 | 1 | 4BR |  | TRUE | FALSE | 5.01 Window leak; resultant damage to interior finishes |  | Wood sill | Stain | Bdrm 2 |  | LF sill/jb | 3" x 3" |  |  | 1 |  | H/S |  |  |  | /Dropbox/Projects/Avala/05 Photos/Avala 2024-10-25 PKE Int_Ext Vis
9
10
11
12
13
14
15
16
17
18